## #PROJECTNAME#
project: | De vloer is lava
calculator:
date: | 2020-01-28
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration (plan) | duration (do) | reflection (check) | transfer (act) | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6
1 |  | Projectplan | M | Shen |  | 3 | 5 |  | Onedrive/Github
2 |  | Pitch presentatie | M | Shen |  | 1 | 3 |  | Onedrive/Github
3 |  | WBS | M | Shen |  | 2 | 4 |  | Onedrive/Github
4 |  | Technisch ontwerp | M | Shen |  | 3 | 4 |  | Onedrive/Github
5 |  | Funtioneel ontwerp | M | Shen |  | 3 | 5 |  | Onedrive/Github
6 |  | Programma van eisen | M | Shen |  | 3 | 5 |  | Onedrive/Github
7 |  | CRPR lijst | M | Shen |  | 1 | 3 |  | Onedrive/Github
8 |  | Test lijst | M | Shen |  | 2 | 3 |  | Onedrive/Github
9 |  | DFD | M | Shen |  | 2 | 4 |  | Onedrive/Github
10 |  | Acceptatietest | M | Shen |  | 2 | 5 |  | Onedrive/Github
11 |  | EvaluatieVerslag | M | Shen |  | 1 | 2 |  | Onedrive/Github
12 |  | Kerntaak 1 | M | Shen |  | 5 | 10 |  | Onedrive/Github
13 |  | Kerntaak 2 | M | Shen |  | 5 | 12 |  | Onedrive/Github
14 |  | Kerntaak 3 | M | Shen |  | 5 | 10 |  | Onedrive/Github
15 |  | Kerntaak 4 | M | Shen |  | 5 | 11 |  | Onedrive/Github
16 |  | OefenPortfolio 1 | M | Shen |  | 20 | 25 |  | Onedrive/Github
17 |  | OefenPortfolio 2 | M | Shen |  | 25 | 30 |  | Onedrive/Github
18 |  | ExamenPortfolio | M | Shen |  | 40 | 50 |  | Onedrive/Github
19 |  | Eindpresentatie | M | Shen |  | 2 | 3 |  | Onedrive/Github
20 |  | Sensoren uitlezen | M | Shen | Als de sensoren niet werken kan je de positie niet uitlezen waar iemand staat. | 10 | 14 |  | Onedrive/Github
21 |  | Ledjes aansturen | M | Shen | Als de ledjes niet werken kan er niet worden aangegeven waar iemand kan staan en waar niet. | 6 | 13 |  | Onedrive/Github
22 |  | Win/Lose condities | M | Shen | Zonder dit zou er geen competitie zijn | 10 | 12 |  | Onedrive/Github
23 |  | LoseEffect | M | Shen | Zonder dit zou je niet weten wanneer je verloren hebt | 20 | 22 |  | Onedrive/Github
24 |  | Randomizer | M | Shen | Zonder een randomizer kan je blijven staan of kan je een patroon lezen | 20 | 24 |  | Onedrive/Github
25 |  | Versneller | M | Shen | Anders kan je voor eeuwig doorgaan | 14 | 15 |  | Onedrive/Github
26 |  | Communicatie aansturings programma | M | Shen | Als dit er niet is kan de vloer niet worden aangestuurd. | 10 | 13 |  | Onedrive/Github
27 |  | Start effect | M | Shen | Zonder weet de gebruiker niet dat het spel is begonnen | 20 | 21 |  | Onedrive/Github
28 |  | Moeilijkheid keuze | C | Shen |  | 40 |  |  | Onedrive/Github
|  | Total: |  |  |  | 280

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma